COMP 10202 Capstone Project Status Report

Name: Olaoluwa Anthony-Egorp

Date: September 19, 2021

Project Progress Status (Delayed, On Schedule, Ahead of Schedule): Delayed

Project Milestones (from the original project proposal or modified):

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Milestone | Estimated Duration | Date | Complete? | Actual Time Spent |
| Setup database schema  Setup GitHub repository  Set up Visual Studio project with authentication  Set up and adjust model for all database tables | 6d | Sep 6-12,2021 | N | 3 hours |
| Develop controller and views for home and about page  Develop controller and views for personal holdings page | 6d | Sept 13-19, 2021 | N | 12 hours |
| Develop the post and delete stock method in the watchlist controller  Develop the edit watchlist in the watchlist controller | 6d | Sept 20-26, 2021 | N |  |
| Develop the views for watch list on the personal holdings page by using stock controller  Deploy to host server (Azure) | 6d | Sep 27-Oct 3, 2021 | N |  |
| Linking application to payment server | 6d | Oct 4-10, 2021 | N |  |
| Develop upgrade user benefits by using payment | 6d | Oct 11-17, 2021 | N |  |
| Develop chart function and views | 6d | Oct 18-24, 2021 | N |  |
| Develop admin pages function and views | 6d | Oct 25-31, 2021 | N |  |
| Develop manager pages functions and views | 6d | Nov 1-7, 2021 | N |  |
| Develop edit user account and user profile functions and views | 6d | Nov 8-14,2021 | N |  |
| Develop the delete and ban account function and views in the admin account page | 6d | Nov 15-21, 2021 | N |  |
| Develop the stock data views for the manager account | 6d | Nov 22-28, 2021 | N |  |
| Follow test plan and go through every task; Work on final presentation | 4d | Nov 29-Dec 5, 2021 | N |  |

Project is delayed due to exporting files from stock tracker to website to populate database with stock table data. Workaround is to finish this for the coming week. All other tasks for Week 1 and Week 2 have been completed. Changes from above timeline will be indicated in yellow

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Milestone | Estimated Duration | Date | Complete? | Actual Time Spent |
| Setup database schema  Setup GitHub repository  Set up Visual Studio project with authentication | 6d | Sep 6-12,2021 | N | 3 hours |
| Develop controller and views for home and about page  Develop controller and views for personal holdings page | 6d | Sept 13-19, 2021 | N | 12 hours |
| Set up and adjust model for all database tables  Develop the post and delete stock method in the watchlist controller  Develop the edit watchlist in the watchlist controller | 6d | Sept 20-26, 2021 | N |  |
| Develop the views for watch list on the personal holdings page by using stock controller  Deploy to host server (Azure) | 6d | Sep 27-Oct 3, 2021 | N |  |
| Linking application to payment server | 6d | Oct 4-10, 2021 | N |  |
| Develop upgrade user benefits by using payment | 6d | Oct 11-17, 2021 | N |  |
| Develop chart function and views | 6d | Oct 18-24, 2021 | N |  |
| Develop admin pages function and views | 6d | Oct 25-31, 2021 | N |  |
| Develop manager pages functions and views | 6d | Nov 1-7, 2021 | N |  |
| Develop edit user account and user profile functions and views | 6d | Nov 8-14,2021 | N |  |
| Develop the delete and ban account function and views in the admin account page | 6d | Nov 15-21, 2021 | N |  |
| Develop the stock data views for the manager account | 6d | Nov 22-28, 2021 | N |  |
| Follow test plan and go through every task; Work on final presentation | 4d | Nov 29-Dec 5, 2021 | N |  |

Modifications to the original Capstone Proposal plan:

* No modifications yet